# HMIHC Background & History

# 2012-2016

J. Farnsworth Consulting, December 31, 2016

## Abstract

Hawaii Maternal and Infant Health Collaborative (HMIHC), founded in 2013, is a public private partnership committed to Improving Birth Outcomes and Reducing Infant Mortality. The Collaborative was developed in partnership with the Executive Office of Early Learning’s Action Strategy with help from the Department of Health and National Governor’s Association. The Action Strategy, an initiative of the Abercrombie Administration in 2012, provided Hawaii with a roadmap for an integrated and comprehensive early childhood system, spanning preconception to the transition to Kindergarten. The Collaborative helps advance goals within the Action Strategy by focusing on ensuring that children have the best start in life by being welcomed and healthy. The Collaborative has completed a strategic plan and accompanying Logic Model, The First 1,000 Days, aimed at achieving the outcomes of 8% reduction in preterm births and 4% reduction in infant mortality by 2018. To date over 120 people across Hawaii have been involved in the Collaborative. These members include physicians and clinicians, public health planners and providers, insurance providers and health care administrators. The work is divided into three primary areas, preconception and inter conception, pregnancy and delivery, the first year of life and coordinated by a cross sector leadership team. Work is specific, outcome driven, informed by data and primarily accomplished in small work groups.

Table of Contents

Abstract	1

I. Roots	3

Executive Office on Early Learning 2012-2014	3

2013 Action Strategy Goal 1 Outcomes	3

Priority Strategies to Achieve Outcomes	4

II. Transition from Action Strategy to Hawaii Maternal and Infant Health Collaborative	4

National Governors Association	4

The HMIHC Framework	6

The HMIHC Outcomes	6

The HMIHC Organizational Structure	6

III. Wrap up of 2014 HMIHC Collaborative Work	8

IV. Wrap up of HMIHC 2015 Collaborative Work	11

V. Wrap up of HMIHC 2016 Collaborative Priorities	13

Appendix A: How it All Connects	15

Appendix B: Core Team 2016	16

Appendix C: Data Info Graphic	17

Appendix D: Logic Model	19

# I. Roots

## Executive Office on Early Learning 2012-2014

In 2012 at the request of The Executive Office on Early Learning (EOEL) and Governor Abercrombie a planning process was designed to address how to impact the indicators that research had found to be significant to early learning. The foundation for much of the research that became part of the design is embedded in a Pathway to Children Ready for School and Succeeding at Third Grade, Lisbeth Schorr, Vicky Marchand, June 2007. As a starting point for planning purposes the framework they proposed was adopted, it was comprehensive of health, safety, family support, early care and education and linked to K-3 education. The framework was populated with baseline local and national data on the indicators to ensure that as the EOEL embarked on a planning process the effort would be informed by data and driven by the outcomes EOEL hoped to achieve.

The Action Strategy was design to address three overarching goals.

- Children’s health (physical, behavioral and oral) and development is on track

- Children are ready for school when they enter kindergarten; and

- Children are proficient learners by third grade.

Six teams were established to develop strategies to move the intermediate outcomes that would achieve the above long term outcomes. They were,

Goal 1: Children are Born Healthy and Welcomed.

Goal 2: Children’s Development is on Track.

Goal 3: Children and families live in safe, stable and supportive homes.

Goal 4: High quality childcare and early education is available, accessible and affordable.

Goal 5: Children and families experience continuous, smooth transitions throughout the birth to age 8 continuum and between different programs and settings.

Goal 6: Teaching and learning strategies in K-3 classrooms are effective.

### 2013 Action Strategy Goal 1 Outcomes

The original team convened through the Action Strategy met during 2012 and put forward the following key objectives to ensure children are born healthy and welcomed. The objectives were incorporated into Governor Abercrombie’s Early Childhood State Plan published in January 2013.

• Women and their families have access to quality health care across their lifespan – with a special emphasis on vulnerable populations.

• Youth defer child bearing until they graduate from high school.

• There are successful birth outcomes

- There is access to high quality family planning services.

- There is a reduction in unintended pregnancies.

- There is access to high quality prenatal/perinatal care (pre conception, birth, postpartum).

• Nurturing, bonding, and attachment are ensured.

### Priority Strategies to Achieve Outcomes

In year one of Action Strategy implementation the following strategies were prioritized.

1a. Improve birth outcomes.

Promote healthy birth and delivery by addressing policies that

1) improve access to continuity of care between pregnancies,

2) reduce elective induction of labor and delivery prior to 39 weeks,

3) reinstate programs that minimize prenatal exposure to tobacco, drugs and alcohol, and

4) address inequity in access to prenatal care for underserved communities.

1b. Optimize early health and bonding through breastfeeding.

Develop and promote a public education campaign; improve maternity care practices such as Baby Friendly Hospital designation and welcome baby baskets with information and resources; educate employers on worksite related breastfeeding policies.

1c. Support adolescent pregnancy deferral.

Include adolescent pregnancy deferral in a comprehensive review of Department of Health and Department of Education curricula that promote adolescent healthy life choices. Look at both content and timing of curricula in light of shifting age of maturation.

# II. Transition from Action Strategy to Hawaii Maternal and Infant Health Collaborative

## National Governors Association

The Action Strategy report and recommendations were published and endorsed by then Governor Abercrombie in January 2013.  In order to further the strategies recommended by the Goal 1 Team.  Members of that team proactively applied to the National Governors Association (NGA) for technical assistance to further the statewide commitment to improving birth outcomes and reducing infant mortality. Hawaii was awarded the one of four technical assistance grants. The NGA technical assistance grant enabled the Team to conduct three statewide strategic planning sessions in the summer and fall of 2013 under the guidance of The Department of Health to develop both a logic model and action plan but most importantly the commitment of a large group of multidiscipline stakeholders to implement the plan.

The three meetings conducted by the Department of Health and Action Strategy with assistance from the National Governors Association were attended by over 100 people, determined outcomes, designed a framework, organizational structure, logic model and work plan. They were held July 17, Oct. 22 and January 30 2014.

The three NGA meetings followed the inquiry outlined below,

Attendees self selected into three teams

- Before Pregnancy

- During Pregnancy and Delivery

- Following Pregnancy/infancy

Teams brainstormed the following questions

- What is it that needs to be changed or improved in our domain in order to reduce infant mortality by 4% and or prematurity by 8% by 2016?

- What are your top three measurable priorities?

  - How it will be measured?

  - How can you best achieve those objectives (what strategies will you use)?

- Who else needs to be involved in order for you to be successful?

## The HMIHC Framework

By January 2014 the scope of work had been determined. It was to encompass The First 1,000 Days; the year before conception, the year of pregnancy and delivery and the first year of life.

## The HMIHC Outcomes

Long Term Outcomes

- Decrease preterm births by 8%

- Decrease infant mortality and morbidity in the first year of life by 4%

Preconception Intermediate Outcomes:

- Improve the proportion of pregnancies that are intended from 48.4% to 53.2%

- Increase the proportion of mothers at healthy weight prior to conception

Pregnancy and Delivery Intermediate Outcomes:

- Decrease smoking during pregnancy from 5% to 3.8%

- Decrease preterm births <37 weeks from 10% to 9.2%

First year of Life Intermediate Outcomes

- Increase infant back to sleep position to 75%

- Increase the proportion of mothers who exclusively breastfeed until 6 mos. to 25.5%

## The HMIHC Organizational Structure

During 2014 there was growing concern that Governor Abercrombie might lose his bid for reelection and be a one term Governor and that the Action Strategy structure and goals might not be continued under a new administration. In order to ensure that the work of Team 1 continued uninterrupted members decided to form an unincorporated organization with a part time paid facilitator through support from the Department of Health. It is this structure that the HMIHC has operated under for the last two years.

Mission:

HMIHC is a public private collaborative effort with the goal of reducing infant mortality by 4 % and improving birth outcomes by 8% in Hawaii by 2018.

Shared Assumptions:

  - Our mission can be best accomplished by coordination of effort in both the public and private sectors.

  - HMIHC is a four pronged approach; a. policy and advocacy, b. the delivery system: clinical and provider practice (includes professional development), c. consumer education and d. the payment system (includes Medicaid, commercial insurance and financing) with the three focus areas of preconception, pregnancy and delivery and infancy, The First 1,000 Days.

  - HMIHC is a trust based collaborative effort in which all members share equal responsibility for success and challenges.

Guiding Principles:

  - Priorities and actions are focused in the mission statement of the collaborative.

  - All work is informed by data; quantitative and qualitative (including both data-based trend analysis and narrative examples from community, both receive equal credibility in considering options for setting priorities).

  - All work addresses disparities and social determinants.

  - Our work addresses the needs of all islands and provides opportunities for all to participate.

Organizational Structure: The governance and administrative structure includes an advisory committee that can serve as advocate for policy change, a core team to provide project management and support for collaborative operations and ad hoc work groups for each goal that implement action plans.

Advisory Board:

Purpose: to assure coordination of effort at a broad policy level

Function: meet semi annually to advise HMIHC on priorities and work plans

Membership: DHS Deputy Director, DOH Deputy Director, Action Strategy Coordinator, representatives from ACOG, HAAP, Healthcare Association of Hawaii

Core Team:

Purpose: To provide coordination of effort across the four domains of policy and advocacy, delivery system, consumer education and outreach and financing.

Work Groups:

- Purpose: Implementation of work plans and to make recommendations to the Steering Committee on process and necessary revision of plans.

- Function: ad hoc committees, determined on an annual basis by Steering Committee. Chairs sit as members of the Steering Committee. Task Forces meet as determined by chair in order to accomplish work plan objectives.

- Membership: open to all interested as determined by chair

# III. Wrap up of 2014 HMIHC Collaborative Work

During 2014 Core Team meetings were held monthly and workgroup meetings as well. In 2014 the HMIHC also became a partner state with the national COIIN initiative to reduce infant mortality. Hawaii, through the HMIHC, participated in three work groups; safe sleep, preconception health-LARC and improved birth outcomes-17P. (see appendix A How it All Connects)

Hawaii Maternal and Infant Health Collaborative Priorities and Milestones

June-December 2014

| Priorities | Measurement | Accomplishments |
| --- | --- | --- |
| Establish an effective HMIH Collaborative that will sustain the work started in 2013 by the National Governors Association Improved Birth Outcomes public private partnership | - quarterly newsletters - continue engagement of key partners; including clinical, data, payers, public health and community providers of care - develop baseline data for key initiatives - develop partnerships to monitor data and progress to outcomes - develop a source of dedicated staffing | A strong joint public-private leadership team was established. Work groups in each domain were established most had established priorities and regular meeting schedules Baseline data was determined and collected Contractor secured for facilitation |
| Effectively link with National COIIN initiatives which will inform Hawaii of best and promising practices | Establish a public private Hawaii COIIN team that will share and inform the broader work of the Collaborative through newsletters, trainings and professional development. | Three COIIN Teams were established; Safe Sleep, 17P and LARC |
| Identification of strategies to reach disparate populations to improve access to preconception and inter conception care | Design a methodology to gain a better understanding of populations at risk and causation. | The HMIHC has yet (year end 2016) determined the best way to address disparities |
| Increase professional and peer support to new parents | - expand Cribs for Kids to neighbor islands - expand utilization of text4baby (% increase) - create strategic alliances to expand home visitation for families with newborns - improve utilization of parent support warm lines, design consistent format - Family Hui focus Infant Safety | Cribs for Kids has expand to Kauai |
| Evaluate group prenatal care models; Centering Pregnancy and prenatal substance use assessment and brief intervention models. | Centering Models - review evaluation research - create a state plan, including cost projections, to bring to scale based on data from high risk communities and populations |  |
|  | Prenatal Substance use cessation - All pregnant women are screened and assessed for substance use and receive brief intervention and referral to treatment if indicated, using validated tools. - A comprehensive system includes tobacco, alcohol, controlled and illicit drugs. - There is provider clarity about reimbursement methodology for both screening, assessment and brief intervention. - There is on going professional development and training in place for providers. - There is one aggregated data system that can be used for program planning and evaluation | Substance cessation Team members met with Lola Irwin and Dr. Cynthia Goto to better understand current efforts underway for smoking cessation and how the Collaborative could help advance this work for the prenatal population. This led to the planning of a joint symposium in October with Dr. Ira Chasnoff hosted by the Collaborative on prenatal substance use cessation. Members of the Core Team met with Dr. Chasnoff on October 30th to discuss his suggestions for how we might implement a statewide program for screening, assessment, brief intervention and referral for substance use. |
| Public awareness of reproductive care benefits under ACA and Quest Integration | - Secure Medicaid reimbursement for immediate post delivery or termination insertion (PPI) of LARC. - Priority is inpatient Medicaid coding for the devise outside of any bundled global maternity payments - The biggest barrier the is cost of the devise | LARC-Summary of work - Writing of a white paper providing background and recommending billing code changes to MedQUEST - Support secured from DOH/FHS chief - Key stakeholder support secured, DHS, ACOG, HAAP |
| Complete neo natal resuscitation training in all birthing hospitals | Initial training will be completed A plan for ongoing training will be in place | All neighbor island training completed |
| Infant Health and Safety |  | There have been three meetings of the Infant Toddler Team to plan a series of four symposia for 2015 Overview: The HMIHC Infant/Toddler Health & Safety Symposia series focuses on multi-disciplinary information sharing to early childhood and health care providers working to provide consistent education and messaging to parents and families of infants and toddlers, especially focusing on information to new mothers. |

.

# IV. Wrap up of HMIHC 2015 Collaborative Work

| Outcome | Content Area | Work Group Priorities | Accomplishments in 2015 |
| --- | --- | --- | --- |
| Formalize HMIHC Organizational Purpose and Structure |  |  | In January 2015 the Core Team held a facilitated retreat to determine the following - Review and Agreement on Purpose and Scope of HMIHC - Determination of effective Organizational Structure - Formation of Rules and Procedures for Conducting Business - Determine Leadership Structure - Current Resources and Sustainability In February recruitment of new members to the Core Team. |
| Increase the rate of intended pregnancies | Pre and Inter Conception Care | Improve access to long acting reversible contraception | Clarified MedQUEST coverage Developed and distributed a coverage chart for clinicians Wrote and presented white paper on the benefits and safety of LARC Presentation at annual ACOG conference |
|  |  | Improve reproductive life planning | Secured partnership with Oregon Reproductive Health Foundation to bring One Key Question to Hawaii |
| Increase Full Term Births | Pregnancy and Delivery | Improve access to 17P | Conducted provider survey to better understand utilization and barriers to access. |
| Improve Birth Outcomes |  | Universal prenatal screening, brief intervention and referral to treatment for prenatal substance use | Completed SBIRT statewide implementation plan Wrote and secured a grant to fund contractor to design system and train providers Contracted with JABSOM to assess SA treatment provider capacity |
| Decrease Infant Mortality | The First Year of Life | Increase safe sleep practices Reinstate child death review and establish maternal mortality review | Expanded Cribs for Kids Program Advocacy team established for CDR/MMR legislative bill passage White paper for testimony background written and vetted |

# V. Wrap up of HMIHC 2016 Collaborative Priorities

| Outcome | Content Area | Work Group Priorities | Accomplishments in 2016 |
| --- | --- | --- | --- |
| Increase the rate of intended pregnancies | Pre and Inter Conception Care | Improve access to long acting reversible contraception | LARC Med QUEST coverage memo released Establishment of hospital pharmacy stocking procedures DOH/DHS collaborative metrics and data tracking |
|  |  | Improve reproductive life planning | One Key Question conducted both clinical and non clinical trainings. Implementation has begun in 4 clinic sites as well as WIC and the home visitation network DOH has made OKQ a priority in the 2016-2018 Strategic Plan |
| Increase Full Term Births | Pregnancy and Delivery | Improve access to 17P | Targeted patient education and outreach through NICU and Home Visitation families |
| Improve Birth Outcomes |  | Universal prenatal screening, brief intervention and referral to treatment for prenatal substance use | HMIHC has successfully found an implementing partner in DOH who has taken over leadership and integration of prenatal SBIRT with the sustainable effort of the general population SBIRT system being developed through a SAMSHA grant. In year 1 of the 2 year grant cycle Hilopa’a has trained 14 physicians, established a partnership with MedQUEST to secure coverage and design a manual of resources and tools for clinicians. |
| Decrease Infant Mortality | The First Year of Life | Reinstate child death review and establish maternal mortality review | CDR/MMR bill successful passed the Legislature and both reviews are actively being implemented through MCHB. A summit was held in June to educate and celebrate the bills passage. |
|  |  | Safe Sleep | Safe Sleep has been spun off from the HMIHC and is being coordinated through DOH and Safe Sleep Hawaii as part of the Hawaii COIIN initiative. |
|  |  | Breastfeeding | The IHS Team has brought together a strong group of advocates to develop a strategic plan to increase lactation support and facilitated longer duration of breastfeeding. |

## Appendix A: How it All Connects

## Appendix B: Core Team 2016

Kimberly Arakaki, HMIHC Co Chair

Maternal and Child Health Branch Chief, Department of Health

808-733-9028

kimberly.arakaki@doh.hawaii.gov

Candice Radner Calhoun, ACSW, L.S.W

Women’s & Reproductive Health Section

MCHB, Department of Health

808-733-9048

Candice.calhoun@doh.hawaii.gov

Linda Chock, M.P.H., R.D

Branch Chief, WIC Branch

Department of Health

808-586-8191

linda.chock@doh.hawaii.gov

Cynthia Goto, M.D.

ACOG Representative

808-292-0456

cindygo@cjgoto.com

Scott Harvey, MD, MS

Associate professor OBGYN Critical Care, Kapiolani Medical Center

Phone:808-203-6580

sharvey@hawaii.edu

Donald Hayes, M.D., M.P.H.

Maternal and Child Health Epidemiologist

Department of Health

808-586-4521

don.hayes@doh.hawaii.gov

Marcy Healey, RN

Quality and Member Relations Improvement Section

Department of Human Services

Med-QUEST Division

Phone: (808) 692-8115

Email: mhealey@dhs.hawaii.gov

Lin Joseph, MPH HMIHC Co Chair

Director of Program Services

March of Dimes Hawaii Chapter

808-973-2152

hjoseph@marchofdimes.com

Althea (Momi) Kamau, MPH

Retired Maternal and Child Health Branch Chief

808-428-3868

momikmau@gmail.com

Lisa Kimura, MBA

Executive Director

Healthy Mothers Healthy Babies

808-737-5805

LisaK@hmhb-hawaii.org

Kathleen Libao-Laygo, RN

Director, Quality & Regulatory Affairs.

Healthcare Association of Hawaii

klibao-laygo@hah.org

Keiko Nitta, MA

Hawaii Department of Health

Early Childhood Comprehensive Systems Grant Coordinator

(808) 733-9079

keiko.nitta@doh.hawaii.gov

Leolinda Parlin

Project Director

Hilopa’a Family to Family Health

808-282-6348

leo@hilopaa.org

Sharon Thomas, MSN, RN

Department of Human Services,

MedQUEST Division

Health Care Services Branch

808-692-8161

sthomas@medicaid.dhs.state.hi.us

Betty Wood, PhD, MPH

Department of Health

808-586-4530

Betty.wood@doh.hawaii.gov

Support:

JoAnn Farnsworth, M.S.

Farnsworth Consulting

808-895-6097

jfarnsworth@hawaii.rr.com

## Appendix C: Data Info Graphic

## Appendix D: Logic Model